## Full OnePager
Strategic Plan 2020-2023
Vision
Provide opportunities for growth and success for our students and community. We are committed to educational experiences that build on the unique environment of the Adirondacks and our institutional values, while nurturing the academic and personal achievement of individuals with diverse backgrounds and aspirations.
Mission
Provide open access to high quality academic programs that prepare students for transfer and career success. Contribute significantly to the enrichment of our communities by cultivating an educated citizenry, a skilled workforce, and opportunities for lifelong learning.
Values
Academic Rigor and Intellectual Curiosity |  | Diversity and Individuality
Accountability, Integrity and Transparency |  | Openness to Change
Compassion and Kindness |  | Shared Governance
Institutional Goals
#1. Provide a meaningful and engaging education that prepares students for transfer or career opportunities. |  | #2. Create and nurture a supportive environment that welcomes diversity and difference and focuses on student success and growth.
Principal Strategies |  | Principal Strategies
A - Faculty and Staff Professional Development | B - New Academic Programs and Certificates | A - Student Success Initiatives | B - Revitalized First-Year Seminar
C - Enhancing Existing Programs and Certificates | D - Facilities to support new and enhanced programs | C - College-wide Diversity Commitments | D - Expand integrated diversity-focused programming and services
#3. Act as a strong and valued partner in the communities we serve. |  | #4. Ensure the financial sustainability of the institution through strengthening enrollment and maximizing use of resources.
Principal Strategies |  | Principal Strategies
A - Expand K-12 and Higher Ed partnerships | B - Continuing Education - K-12 and Licensed Professionals | A - "Right-size" College operations to enrollment/ finance and "work smarter" improving efficiencies across areas | B - Reconfigure organizational structure - faculty and staff size matches instructional, operational and strategic needs
C - Expand Partnership with St. Regis Mohawk Tribe | D - North Country CC - Workforce Development Partnership | C - Develop prior learning assessment framework and process | D - New revenue streams to support mission and student experience
Model and Approach to Strategic Planning
At the core of the strategic plan is student success which is expressed through our academic programs and certificates - the mission of the College. Relatedly, as students realize success, so too does the College and the communities we serve. The institutional goals are the ways the College realizes its vision and carries out its mission, with actions and activities guided by its values. The faculty create, deliver, assess and improve the curriculum. Other areas of the institution support student learning, the student experience, and teaching excellence. Each area adds value to and supports the student experience, while the efforts of some areas/ departments are threaded through all operations.
Areas/Departments
Academics |  | Financial Operations
Enrollment |  | Human Resources
Facilities |  | Information Technology/Institutional Research
Financial Aid |  | Student Life

## OnePager Goal 1
Institutional Goal #1 | Provide a meaningful and engaging education that prepares students for transfer or career opportunities.
Principal Strategies | A - Faculty and Staff Professional Development |  | B - New Academic Programs and Certificates
Initiatives | i. New Faculty Training Program | ii. Ongoing Professional Development | i. Entrepreneurship Certificate | ii. Health Care Admin track
| iii. Faculty and Staff Positions and Patterns | iv. Commitment to Diversity, Equity and Inclusion | iii. Cybersecurity | iv. Teacher Asst Certificate?
|  |  | v. Wastewater Technology? | vi. Med Office Asst?
|  |  | vii. Green Technologies? | viii. Childcare?
|  |  | ix. Other Healthcare (Public Health)? | x. AOS Programs?
| C- Enhancing Existing Programs and Certificates |  | D - Facilities to support new and enhanced programs
Initiatives | i. Program analysis and realignment to fit within workforce needs and student desires | ii. Reinvest in health careers and health science programs where a) workforce needs exist, b) student desires exist, and c) our capacity to instruct or recruit faculty exists. | i. Create 1-2 state-of-the-art classrooms to support high-flex model of teaching and learning | ii. Work with Nursing Department to modernize Nursing Labs on all three campuses
| iii. Focus on data-driven decision-making with improved IR functionality | iv. Increase enrollment in existing programs where student interest and regional demand exist
v. Expansion of low-residency programs
Related Institutional Goals | #2 | #3 | #4
Related Principal Strategies | A. Student Success Initiatives (onboarding, earlier advisement, advising infographics) | A. Expand partnerships with area colleges | A. "Right-size" College operations to enrollment/finance and "work smarter" improving efficiencies across functional areas
| B. Revitalized First-Year Seminar | B. Provide Continuing Education for Licensing Programs (healthcare, childcare, education) and K-12 Educators | B. Reconfigure organizational structure so that employee (faculty and staff) size matches instructional, operational and strategic needs
| C. Commitment to Diversity, Equity and Inclusion | D. Expand workforce development and continuing education activities | C. Develop prior learning assessment framework and process
D. New revenue streams to support mission and student experience

## OnePager Goal 2
Institutional Goal #2 | Create and nurture a supportive environment that welcomes diversity and difference and focuses on student success and growth.
Principal Strategies | A. Student Success Initiatives |  | B. Revitalized First-Year Seminar
Initiatives | i. Develop and map out College Navigator/ Onboarding restructuring proposal | ii. Earlier advisement to help students be better informed and plan for their future | i. Replace and refresh CSP 100 College Success Seminar with more current and topical content and delivery | ii. Common Read integration into First-Year Seminar
iii. Develop infographics for students to use to visualize academic pathways to careers and transfer opportunities.
| C. College-wide Diversity Commitments |  | D. Expand integrated diversity-focused programming and series
Initiatives | i. Regular Climate Assessment | ii. Preferred Name Policy | i. Common Read | ii. North Country Live - Continuing Education series
| iii. Accessibility Assessment | iv. Explore inclusion of diversity commitment assessment as part of program review | iii. Self-paced diversity course
Related Institutional Goals | #1 | #3 | #4
Related Principal Strategies | A. Faculty and Staff Professional Development | A. Expand K-12 and Higher Ed partnerships | A. "Right-size" the College operations to align with changing enrollment and financial picture
| B. New Academic Programs and Certificates | C. Expand Partnership with St. Regis Mohawk Tribe | B. Reconfigure organizational structure so that employee (faculty and staff) size matches instructional, operational and strategic needs
| C. Enhancing Existing Academic Programs and Certificates | D. Expand workforce development and continuing education activities | C. Develop prior learning assessment framework and process
D. Facilities to support new and enhanced programs

## OnePager Goal 3
Institutional Goal #3 | Act as a strong and valued partner in the communities we serve.
Principal Strategies | A - Expand K-12 and Higher Ed partnerships |  | B - Continuing Education - K-12 and Licensed Professionals
Initiatives | i. Establish regional college consortiums with opportunities for shared services and cross-institutional enrollment | ii. Development of new program collaborations, co-location of 4-year institutions on campus and specific shared service agreements | i. Provide Continuing Education for Licensing Programs (healthcare, childcare, education) | ii. Provide Continuing Education Programs for K-12 Teachers
| iii. Expanded 2+2 agreements, articulation agreements, and increased transfer opportunity for students. |  | iii. Offer More Training Programs (i.e. Business Dept. current plan for offering professional skills training)
| C - Expand Partnership with St. Regis Mohawk Tribe |  | D - North Country CC - Workforce Development Partnership
Initiatives | i. Strengthen and nurture the working relationship with the St. Regis Mohawk Tribe including exploring other ways to support the academic and continuing educational needs of tribal members | ii. Working with St. Regis Mohawk Tribe's education partners, expand offerings that best serve student and tribal needs | i. Assess need for a point-person to lead Continuing Ed (CE), Workforce Development (WFD) and Career and Technical Education (CTE) area permanently. | ii. Continue to host North Country CC-Workforce Development Partnership with county, tribal and regional workforce representatives, identifying employment needs
iii. Increase partnerships with area employers and identify business training and continuing education needs that the college can provide (e.g. IP, St. Joe’s, Mtn Lakes, Elderwood)
Related Institutional Goals | #1 | #2 | #4
Related Principal Strategies | A. Faculty and Staff Professional Development | A. Student Success Initiatives (onboarding, earlier advisement, advising infographics) | A. "Right-size" the College operations to align with changing enrollment and financial picture
| B. New Academic Programs and Certificates | B. Revitalize First-Year Seminar | B. Reconfigure organizational structure so that employee (faculty and staff) size matches instructional, operational and strategic needs
| C. Enhancing Existing Academic Programs and Certificates | C. College-wide Diversity Commitments | C. Develop prior learning assessment framework and process
D. Facilities to support new and enhanced programs

## OnePager Goal 4
Institutional Goal #4 | Ensure the financial sustainability of the institution through strengthening enrollment and maximizing use of resources.
Principal Strategies | A - "Right-size" College operations to enrollment/finance and "work smarter" improving efficiencies across functional areas |  | B - Reconfigure organizational structure - faculty and staff size matches instructional, operational and strategic needs
Initiatives | i. Program analysis and realignment to fit within workforce needs and student desires | ii. Identify additional operational efficiencies leading to reduced costs | i. Develop and map out College Navigator/ Onboarding restructuring proposal | ii. Create more nimble staffing pattern, leveraging strengths and contribute talents in new ways
| iii. Analysis of administrative, campus and support operations leading to increased efficiencies | iv. Explore more cost-effective solutions related to printing
| C - Develop prior learning assessment framework and process |  | D - New revenue streams to support mission and student experience
Initiatives | i. Assess cost-benefits of adopting prior learning assessment framework for students and college | ii. If feasible, develop prior learning assessment implementation plan, process and policy. | i. Partner with NCCC Foundation and NCCC Association to develop strategies to diversify funding to support mission of the College. | ii. Assess need and funding to support grant writer position.
iii. Explore opportunities to strengthen the Board of Trustees and the Foundation Board in their fundraising capacities, including collaborative fundraising efforts.
Related Institutional Goals | #1 | #2 | #3
Related Principal Strategies | A. Faculty and Staff Professional Development | A. Student Success Initiatives (onboarding, earlier advisement, advising infographics) | A. Expand K-12 and Higher Ed partnerships
| B. New Academic Programs and Certificates | B. Revitalize First-Year Seminar | C. Expand Partnership with St. Regis Mohawk Tribe)
| C. Enhancing Existing Academic Programs and Certificates | C. College-wide Diversity Commitments | D. Expand workforce development and continuing education activities

## Full Plan - Draft
Feb 9, 2021
Priority | Status | Why this initiative? | Institutional Goal Alignment | Principle Strategy | Initiatives | Strategic Actions/Tactics - 1st Year | Strategic Actions/Tactics - 2nd Year | Expected Outcomes | Primary Lead(s) | Administrative Supports | Academic Supports | Business Office/Bursar | Enrollment | Facilities | Financial Aid | IT/IR | Human Resources | Student Affairs | Budget | Assessment of Progress*
|  |  | 1A | Faculty and Staff Professional Development
[5 empty] | 1Ai. New Faculty Training Program | Identify necessary elements to orient new faculty members in regards to the College's educational philosophy; its mission, vision, values; pedagogical supports, course/syllabus development, and assessment of student learning outcomes Create a template of a program (e.g. checklist) with corresponding supports (e.g. pre-recorded videos) to help deliver these | Launch new faculty training program, assess impact, and make changes as appropriate. | Establish effective onboarding and training program to equip new full-time and part-time faculty members with academic/instructional tools to more effectively teach. | Academic Affairs/Human Resources | Identify budget and human resources to establish training program. |  | NA |  | Consult with with AA to ensure sufficient working areas/offices to support new faculty.
[6 empty] | Identify onboarding needs of new faculty members beyond the academic area including onboarding, benefits, mandatory trainings | Launch new faculty training program, assess impact, and make changes as appropriate. | Ensure new full-time and part-time faculty members have a comprehensive understanding of benefits and training expectations.
[5 empty] | 1Aii. Ongoing Professional Development | Identify faculty members to the lead adoption of and subsequent training in teaching modalities including high-flex Resource professional development opportunities for teaching modalities, including high-flex, enabling training to take place | Expand opportunities to include College Bridge instructors. | Expanded use of professional development opportunities to improve teaching and/or develop new competencies which can enhance existing or create new program options | Academic Affairs/Human Resources | Dedicate funding to professional development. Working with academic departments, identify strategic PD needs. |  | NA |  | NA
[6 empty] | Identify critical areas of professional development in pedagogy, both technological and behavioral | Develop training calendar and other opportunities for specific and universal professional development. Expand opportunities to include College Bridge instructors.
[5 empty] | 1Aiii. Faculty and Staff Positions and Patterns | Identify areas where increased flexibility in faculty and staff are possible to advance the mission (e.g. faculty in recruitment roles; faculty ambassadors to K-12; new program development release time) | Create greater flexibility in faculty and staff position descriptions to allow for flex into new areas (e.g. faculty into recruitment roles) | Creation of a more nimble faculty and staff able to leverage strengths and contribute talents in new areas/ways. | Academic Affairs/Human Resources | Develop proposals, share with collective bargaining units, gather input from President's Council and others. |  |  |  | Work with Academic Affairs on need for traveling faculty office spaces, adjunct faculty office spaces and full-time faculty office spaces in post-COVID-19 world. Plan and ready facilities to support these changes
[6 empty] | Assess need for/changes to staffing pattern in post-COVID-19 world including number of traveling faculty members, online offices, | Negotiate with our collective bargaining units (CBUs) on new staffing patterns, work expectations, and position descriptions to better prepare for post-COVID-19 world | Develop expectations for a new working environment allowing for extended remote work and instruction. | Academic Affairs/Human Resources | Negotiate with CBUs
[5 empty] | 1Aiv.Commitment to Diversity, Equity, and Inclusion | See 2 Ci Conduct climate assessment and use results to develop actions to improve climate | See 2 Ci | Establish regular cycle of climate assessment and use of results to improve campus climate | Student Affairs/Academic Affairs
[6 empty] | Conduct accessibility assessment and use results to develop actions to improve climate |  | Establish regular cycle of accessibility assessment and use of results to improve campus climate
Develop and adopt Common Read, integrated into First-Year Seminar
|  |  | 1B | New Academic Programs and Certificates
|  | SP1, SP2, SP3 |  |  | 1Bi. Entre Cert | Register program with NYSED via SUNY Prepare for recruitment of new students Upon approval, launch recruitment efforts including marketing to area BOCES | Launch program and assess Identify non-credit opportunities Identify prior learning assessment credits that can be awarded (linked to experience) | Year 1 Recruitment = 10 students Year 2 Recruitment = 15 students | Academic Affairs/Academic Departments/Enrollment | College Navigator Restructuring | Ensure tutoring resources are available for new content area Assess for unique ADA/504 needs |  | Assess student interest/demand Assist with articulation possibilities |  | Assist with ensuring financial aid process between two institutions is seamless | Work with department regarding new/enhanced IT needs support integration of student grades from one SUNY institution to NCCC | Possible need for part-time faculty member |  | Insert costs….
|  | SP1, SP2, SP3 |  |  | 1Bii. Health Care Admin | Register program with NYSED via SUNY Secure faculty member to teach new courses Prepare for recruitment of new students Upon approval, launch recruitment efforts including with area BOCES and health care organizations | Formalize articulation agreement with SUNY Canton Explore options for dual-marketing with SUNY Canton | Year 1 Enrollment = 10 students Year 2 Enrollment = 15 students | Academic Affairs/Academic Departments/Enrollment |  | Ensure tutoring resources are available for new content area Assess for unique ADA/504 needs
[5 empty] | 1Biii. Cybersecurity | Determine demand, interest and capacity to deliver within mission Develop program aligned with Herkimer CC program Jointly work with BUS/CRJ to develop program Work with Herkimer CC to jointly register program Create program budget Move through NCCC shared governance process | Register program with NYSED via SUNY Secure faculty member to teach new courses Prepare for recruitment of new students Upon approval, launch recruitment efforts | Year 1 Enrollment = 10 students Year 2 Enrollment = 15 students | Academic Affairs/Academic Departments/Enrollment |  | Ensure tutoring resources are available for new content area Assess for unique ADA/504 needs |  |  | Possible configuration of new classroom
[5 empty] | 1Biv.Teaching Assistant Certificate | Determine demand, interest and capacity to deliver within mission Jointly work with HUM/SS Depts to develop program Create program budget Move through NCCC shared governance process | Register program with NYSED via SUNY Secure faculty member to teach new courses Prepare for recruitment of new students Upon approval, launch recruitment efforts | Launch affordable and desirable teaching assistant certificate as evidenced by enrollment Year 1 Enrollment = 10 students Year 2 Enrollment = 15 students | Academic Affairs/Academic Departments/Enrollment |  | Ensure tutoring resources are available for new content area Assess for unique ADA/504 needs
|  | SP1, SP2, SP3 |  |  | Other Potential New Programs | Evaluate Labor Markets and Create Certificate Programs Based on Needs
|  | SP1, SP2, SP3 |  |  | 1Bv. Wastewater Operator | see 1Biv. | see 1Biv. | Explore options of adding wastewater operator coursework, track or program linked to Envir Sci/Env Studies | Academic Affairs/Academic Departments/Enrollment |  |  |  |  | Possible configuration of new classroom
[5 empty] | 1Bvi. Medical Office Asst | see 1Biv. | see 1Biv. | Explore options of adding Med Office Asst with Business and Health Science | Academic Affairs/Academic Departments/Enrollment |  |  |  |  | Possible configuration of new classroom
[5 empty] | 1Bvii. Green Technologies | see 1Biv. | see 1Biv. | Assess need and ability to offer green technologies programs. | Academic Affairs/Academic Departments/Enrollment
[5 empty] | 1Bviii. Childcare | see 1Biv. | see 1Biv. | Explore options of adding childcare certificate with Human Services | Academic Affairs/Academic Departments/Enrollment
[5 empty] | 1Bix. Other Healthcare (Public Health) | see 1Biv. | see 1Biv. | Explore options of adding AS Public Health with Health Science | Academic Affairs/Academic Departments/Enrollment
|  | SP1, SP2, SP3 |  |  | 1Bx. AOS Programs | see 1Biv. | see 1Biv. | Assess need and ability to offer AOS programs. | Academic Affairs/Academic Departments/Enrollment
|  | SP1, SP2, SP3 | 1C | Enhancing Existing Programs and Certificates
|  | SP1 | #1, #4 |  | 1Ci. Program analysis and realignment to fit within workforce needs and student desires - grounded in data | Create alternate/standardized metric for economic analysis of programs to maximize resources and align revenue/expenditures links to mission, and value added to counties | Increase enrollment capacity of selective programs | A standardized tool to evaluate program health | Administration/Academic Affairs/Academic Departments
|  | SP1 |  |  |  | Evaluate whether program(s) are mission-critical | Deactivate under-enrolled programs | A standardized and transparent process leading to deactivation/discontinuance of programs
[6 empty] | Evaluate costs per: student/program/campus and overall costs/benefits | Where feasible, consolidate programs and leverage online environment to build capacity (e.g. AAS Computer Graphics on two campuses to one) | Reduction of under-enrolled sections and programs | Administration/Academic Affairs/Academic Departments
|  | SP1, SP3 |  |  |  | Identify loss-leaders and profit-generators and focus on those growing and with stable enrollment | Adjust faculty/staff size relative to programs | Strengthened programs | Administration/Academic Affairs/IR
|  | SP1, SP3 |  |  |  | Follow up with identified programs and how to move forward with timelines
[6 empty] | Identify need for in-demand trades that align with existing certificates | Certificate programs: align in-demand trades with quickly completed certificates | Development of new or revitalized certificate programs linked to in-demand trades | Academic Affairs/Academic Departments/Enrollment
|  |  | #1, #4 |  | 1Bii. Reinvest in health careers and health science programs where a) workforce needs exist, b) student desires exist, and c) our capacity to instruct or recruit faculty exist | Explore increasing clinical capacity and training opportunities in existing health care programs: needs assessment, student demand, cost/benefit analysis | Depending on year 1 findings, either move towards expanding existing health care enrollments or take no further action | Determine need and opportunity to expand existing health care programs. | Administration/Academic Affairs/Enrollment |  |  |  |  | Work with Academic Affairs, Nursing Dept and Health Sciences on plan to update nursing labs
|  | SP 1 | #4 |  | 1Biii. Focus on data-driven decision-making with improved IR functionality | Develop weekly IR reporting dashboards | Identify external data sources to determine student interest in programs and in-demand career paths | Improved access to data | IR/Administration/Academic Affairs/Enrollment
|  | SP 1, SP 3 |  |  |  | Better resource (funding and staff) and increase access to institutional research data | With assistance from IR, evaluate new staffing pattern and assess effectiveness for student and faculty/staff support. | Increased numbers of trained staff on use of data reporting tools | IR/Administration/HR
|  | SP 1, SP 3 |  |  |  | Use data for decision making in assessment of programs, program review, grant applications, marketing and enrollment efforts |  | Timely and more readily accessible data sources | IR/Administration
|  | SP2, SP3 | #1, #4 |  | 1Biv. Increase enrollment in existing programs where student interest and regional demand exist | Identify additional ways to effectively market current programs in our local communities. | Assess novel marketing strategies for those programs identified | Increased interest and enrollment in targeted programs using novel marketing strategies, or, find evidence that programs have lost market interest and use information to either refresh or deactivate program(s) | Enrollment |  |  |  |  | Work with AA and IT to identify and update classrooms on each campus to support high-flex teaching needs.
[6 empty] | Identify 4-5 programs to market where student interest and regional demand exist | Use lessons learned from prior year to improve marketing strategies of existing programs |  | Enrollment/Academic Affairs |  |  |  |  | Develop alternative facilties plan to address smaller budget facilities upgrades that position the campus gradually and continuously improve facilities in absence of significant funding from sponsors.
[6 empty] | Develop 2-3 new strategies to market current programs in our service area |  |  | Enrollment
[6 empty] | Reach out to Labor Unions such as NYSCOBA and Federal CO unions to Partner and Offer Certificates/Degrees to Employees | Development of select pathways for regional employers staff to academic programs and certificates | Assess needs of regional employers and, where needs exist, develop select pathways for individuals to existing programs. | Academic Affairs/Enrollment
[6 empty] | Determine needs of these regional employers and work with respective departments to develop pathways for these individuals |  |  | Academic Affairs/Enrollment
|  |  | #1, #4 |  | 1Bv. Expansion of low-residency programs | Assess Spring 20, Fall 20 and Spring 21 data for student interest and performance in low-residency programs | If determined feasible, seek out any approvals required and launch new low-residency delivery of existing programs. | Determine demand, capacity and opportunity to deliver low-residency programs in cost-effective ways and, where feasible, launch them. | Academic Affairs/IR/Academic Departments
[6 empty] | Work with appropriate departments to develop selective new low-residency options where demand, interest and capacity to deliver intersect | If feasible, work with departments to prepare for marketing and launch of new programs. | Effective marketing and subsequent enrollment and launch of new programs. | Academic Affairs/IR/Academic Departments/Enrollment
[6 empty] | Determine if there are any required additional approvals from NYSED or MSCHE |  |  | Academic Affairs
|  |  | 1D | Facilities to Support New and Enhanced Programs
[5 empty] | 1Di. Create 1-2 state-of-the-art classrooms to support high-flex model of teaching and learning | Designate 1-2 classrooms on each campus to be upgraded to support high-flex teaching and learning | Designate 1-2 classrooms on each campus to be upgraded to support high-flex teaching and learning | Development of two classrooms on each campus to support high-flex teaching and learning. | Facilities/Academic Affairs |  |  |  |  | Work with AA and IT to identify and update classrooms on each campus to support high-flex teaching needs.
[6 empty] | Identify initial financial resources to support upgrade including evaluating for capital reimbursement. | Develop plan for sustainability of these classrooms and consider expansion | Link these investments to plan for upgrading and standardization of instructional technology across the college and to capital facilities planning. | [5 empty] | Develop alternative facilties plan to address smaller budget facilities upgrades that position the campus gradually and continuously improve facilities in absence of significant funding from sponsors.
[6 empty] | Gather input from faculty, IT, and others on rooms, design elements to inform plan | Gather input from faculty, IT, and others on rooms, design elements to inform plan
[6 empty] | Upgrade at least one (1) room on each campus. | Using learning from year one, upgrade at least one (1) additional classroom on each campus
[5 empty] | 1Dii. Work with Nursing Department to modernize Nursing Labs on all three campuses | Identify most creative means to modernize existing lab space to best support clinical teaching and learning for PN and ADN students | Upgrade at least one (1) lab over the summer and use faculty and student input to inform next round. If possible, make second upgrade over winter break and third during the upcoming summer break. | Development of two updated, state-of-the-art clinical simulation labs that support student learning and success in clinical setting and when placed in workforce. | Facilities/Academic Affairs |  |  |  |  | Work with Academic Affairs, Nursing Dept and Health Sciences on plan to update nursing labs
Identify particular needs (e.g. simulation) and include planned headwall simulators as part of project
[6 empty] | Develop budget and sources of financing to support project | Identify how best to sustain upgrades and plan for future ones. | Development of a plan, linked to Nursing program review, evaluating labs and identifying resources to keep them operating effectively.
[6 empty] | Develop priority plan for which campus to modernize first | Use learnings from prior year's modernization efforts to inform this years.
|  |  | 2A | Student Success Initiatives
|  |  | #2, #4 | These are linked to and we'll want reference to Retention/ Completion/ Placement | 2Ai. Develop and map out College Navigator/ Onboarding restructuring proposal. | Work with various areas and supervisors to identify the existing flow of student onboarding, from application to first week of classes. Use input to improve student experience and help them be better prepared to start classes. Identify new operational efficiencies and work with CBAs and employees to restructure positions/work to better serve students. | Launch Navigator/Onboarding proposal. | Restructure administrative and student support positions, creating student college navigators leading to improved supports for and preparation of students as they begin or return to college. Improved persistence, retention and completion rates of students as students are better equipped to engage tools for success. Improved delineation of processing tasks leading to improved efficiencies in data-processing. Improved satisfaction among employees as operational inefficiencies are reduced, positions become better calibrated to changing technological conditions (e.g. reduction in processing needs), and employees are encouraged to develop and build more skills | Administration/Academic Affairs/Enrollment/HR/Student Affairs
[5 empty] | 2Aii. Improved advising resources to help students be better informed and plan for their future | Advisement Committee will review and identify additional gaps in advising resources Advisement Committee will recommend changes and improvements in program webpages and college catalog. Integrate course catalog with academic program pages, creating a more dynamic and user-friendly experience for students to access and reference. | Review and refine advising resources. Develop a process for ongoing updates prior to each new academic year. | Improved understanding by students of possibilities and pathways associated with various fields of study. Modest improvement in completion by students as they will have a more informed sense of and commitment to their academic choices. | Academic Affairs/Advisement Committee
[5 empty] | 2Aiii. Develop infographics for students to use to visualize academic pathways to careers and transfer opportunities. | CTE Coordinator to lead task force of faculty and enrollment staff to identify 3-4 CTE pathways to focus on based on student interest and demand. Develop a template to map out visual pathways for career and transfer opportunities withing those programs. Gather input from full faculty and pilot use with newly recruited and first year students. | Based on input from students, faculty, and staff modify the template as need be. Expand model to all programs. Develop procedures to include annual review and update of the document, centrally located and easily accessible. | Improved understanding by students of possibilities and pathways associated with various fields of study. Modest reduction in time-to-completion by students as they will have a more informed sense of where their academic choices and take them. | CTE Coordinator/Academic Departments/VPAA/Student Affairs
Revitalized First-Year Seminar
[5 empty] | 2Bi. Replace and refresh CSP 100 College Success Seminar with more current and topical content and delivery | The LAC Coordinator for our Malone campus will convene a task force composed of faculty, academic support and student affairs employees to map out the particulars of a first-year seminar. That group will develop a proposal to include content, delivery methods/modalities, assessment measures and the like. If the seminar is credit-bearing, work with the various entities (academic departments, Curriculum Committee, College Senate) to obtain support to offer within programs, approval to include in curriculum, and assistance in recruiting students. If seminar is not credit-bearing, determine how students will be recruited to the course and how the costs will be offset. | Launch updated First-Year Seminar. Informally assess delivery and student engagement throughout the semester. Formally assess student performance at semester's end. Make any recommended changes based off of first semester and offer again in spring term. | Improved student persistence, retention, and completion as students will be better prepared and/or improve their technological, behavioral and cognitive skills to meet the demands of a college education. Increased enrollment in and satisfaction with the course by students. | LAC Coordinator - Malone Campus/First-Year Seminar Task Force/Academic Affairs
[5 empty] | 2Bii. Common Read integration into First-Year Seminar | See 2Di below | Take learnings from Common Read experience and fold into First-Year Seminar. | Expanded
College-wide Diversity Commitments
[5 empty] | 2Ci. Regular Climate Assessment | See 1Aiv Identify a climate assessment instrument to be used. This is currently being explored with the student affairs group within the SUNY community college sector. Identify budget line to support adoption of said plan if needed. Set up plan to administer the assessment for 2021-22 year and establish a sustainable cycle of ongoing administration. If possible, align cycle opposite Student Opinion Survey administration. | See 1Aiv Administer survey and analyze survey results. Mine results to identify areas needing attention and resources, leading to development of initiatives to address needs. | See 1Aiv Long-term: development of an ongoing cycle of climate assessment and use results for continuous improvement in realizing diversity commitments and goals. Short-term: deliver and analyze survey, using results to inform changes. | Student Affairs
[5 empty] | 2Cii. Preferred Name Policy | Continue movement of policy through shared governance system, including student input. Present the policy to the administration and Board of Trustees for approval. | Adopt and implement policy and make adjustments to its operations as issues arise. | Students would be able to identify and present themselves within our community by their preferred name. | Student Affairs/Registrar
[5 empty] | 2Ciii. Accessibility Assessment | Recruit a small interdisciplinary task-force to conduct an accessibility assessment of physical and electronic/digital locations. Identify instrument and process for conducting said assessment. Identify budget and other resources needed to conduct assessment. | Conduct assessment and analyze results by campus and by building/location (including digital/electronic). Identify high-priority items to place attention and resources to. Develop plan to address those needs and for continuing to assess and improve accessibility. | Establish an accessibility baseline and plan to continuously assess and improve. Improve accessibility to physical locations and buildings as well as electronic/digital resources (i.e. website, library, course materials). | Student Affairs/Academic Affairs/ADA-504 Coordinator/Facilities
[5 empty] | 2Civ. Explore inclusion of diversity commitment as part of program review. | Develop list of diversity commitments with illustrations of where they are currently being expressed and possibilities to do so in other areas. Conduct college-wide town hall meeting to explore possibilities of institutionalizing diversity commitments by including them as part of program review, academic and other. Request academic and other departments to consider and provide input on how this may be work within their program review cycles. | Identify or develop a rubric for how diversity commitments can be folded into program activities/plans/operations. Adopt a rubric for how diversity commitments can be assessed within program review. Work with individual departments to test the instruments and report out findings. | Assess institutional interest in broadening assessment of diversity commitment into program review. Use findings to improve carrying out diversity commitments. | Student Affairs/Academic Affairs
Expand integrated diversity-focused programming and services
[5 empty] | 2Di. Common Read. | Led by the Interim VP for Student Affairs, the College's Diversity Task Force will select a common read and will encourage faculty and departments to find ways to integrate it into their courses/operations. Engage key college structure/leader (e.g. President's Council) to begin the process and discuss as a unit. Move Common Read out to faculty and staff more broadly and create corresponding times to delve more deeply into the topics under consideration and identify what, if any, changes we can consider. | Assess the impact and perceived value of the common read for the faculty and staff. Explore recommended changes to our operations in regards to strengthening our ability to engage, support and improve upon our commitments to diversity across the college. Use these assessments to plan for and improve the process for the next year, if found valuable. | Increased appreciation by the college community on the value of an integrated and focused set of diversity-related activities and services. Specially for the common read, an improved understanding a diverse perspective which leads to more compassion for and towards those of different backgrounds who work and study at the College. Increase cultural competency among workforce and student body. Gain ability to recognize inequities and implicit biases that may be present in college operations and affect the student and workforce experience. | VP for Student Affairs/Diversity Task Force
[5 empty] | 2Dii. North Country Live - Continuing Education Series | Led by the Opportunities group and working in conjunction with Academic Affairs and Student Affairs, build upon the very successful series from Summer 20 (the African-American Experience in the Adirondacks), and Fall 2020 (the St. Regis Mohawk Tribe, past and present) |  | Increased recognition and celebration of diversity in our communities. Provide diversity-related programming to our campus and the broader communities. | Opportunities Group/Student Affairs/Academic Affairs
2Diii. Create and launch a self-paced diversity course for faculty and staff.
Expand K-12 and Higher Ed partnerships
[5 empty] | 3Ai. Establish regional college consortiums with opportunities for shared services and cross-institutional enrollment | Set up initial meetings with Associated Colleges of St. Lawrence, PSC, Clinton CC, SUNY Plattsburgh, SUNY Empire | Explore opportunities to partner in areas where we or they have greater expertise or strengths including academic program collaborations, library services, shared services and cross-institutional enrollment | Establish regional college consortiums with opportunities for shared services and cross-institutional enrollment Explore merger possibilities (e.g. Clinton CC) if consortium agreements and shared services bear fruit | Administration/Academic Affairs
[5 empty] | 3Aii. Development of new program collaborations, co-location of 4-year institutions on campus and specific shared service agreements | Identify new program collaborations to better serve student interest and regional demand - Cybersecurity with Herkimer CC - Health Care Admin with SUNY Canton - ??? with Clinton CC | (see above under New Programs) | (see above under New Programs) | Administration/Academic Affairs/Enrollment |  |  |  |  | Work with AA on the facilities needs should co-location of operations become viable.
[6 empty] | Explore 4-year schools to our campus (on campus BA degrees though other schools) | If feasible, establish agreement and work towards establishing co-location of baccalaureate programs | Determine, and if financially viable, lay groundwork for co-location of 4-year institution on one or more of our campuses
[5 empty] | 3Aiii. Expanded 2+2 agreements, articulation agreements, and increased transfer opportunity for students. | Assess status and success of current articulation/2+2 agreements | Develop, update and expand articulations agreements, other partnerships and dual registration opportunities with regional colleges | Expanded 2+2 agreements, articulation agreements, and increased transfer opportunity for students. Establish a process for maintaining, tracking, and marketing those agreements to and for students | Student Affairs/Enrollment/Academic Affairs
Continuing Education - K-12 and Licensed Professionals
[5 empty] | 3Bi. Provide Continuing Education for Licensing Programs (healthcare, childcare, education) | Defer until year 2 | Assess needs for continuing education and college's ability to deliver in cost-effective, revenue enhancing way | Use assessment data to inform next steps. | Academic Affairs/CTE Coordinator
[5 empty] | 3Bii. Provide Continuing Education Programs for K-12 Teachers | Defer until year 2 | Assess needs for continuing education and college's ability to deliver in cost-effective, revenue enhancing way | Use assessment data to inform next steps. | Academic Affairs
[5 empty] | 3Biii. Offer More Training Programs (i.e. Business Dept. current plan for offering professional skills training) | Defer until year 2 | Assess needs for continuing education and college's ability to deliver in cost-effective, revenue enhancing way | Use assessment data to inform next steps. | Academic Affairs/Departments
Expand Partnership with St. Regis Mohawk Tribe
[5 empty] | 3Ci. Strengthen and nurture the working relationship with the St. Regis Mohawk Tribe (SRMT) including exploring other ways to support the academic and continuing educational needs of tribal members | Continue to invite SRMT representatives and members to participate in campus, program and college-wide advisory groups/boards. Identify areas of need, including workforce training, continuing education, and related areas where the College could be helpful. Explore opportunities for member of the SRMT to serve on the College Foundation Advisory Council. | Offer reciprocal willingness to assist and serve on advisory councils that would be helpful to the SRMT. Collaborate with SRMT WFD and College WFD to provide any training and continuing education where identified. Invite members of the SRMT to serve on the College Foundation Advisory Council. Invite a member of the SRMT to be a commencement speaker. | Be known as a college committed to the success of St. Regis Mohawk Tribal community as evidence by partnership and working relationship | Academic Affairs/Student Affairs/ President's Office
[5 empty] | 3Cii. Working with St. Regis Mohawk Tribe's education partners, expand offerings that best serve student and tribal needs | Continue partnership with SRMT Education Department to identify course offerings, marketing, and recruitment of students. Assess course offerings, student performance, and student interest to inform the following year's schedule and supports. | Working with SRMT Education Department, expand offerings where student interest and college capacity align. Delivery courses, assess course offerings, student performance, and student interest to inform the following year's schedule and supports. | Increase the number of courses offered on the St. Regis Mohawk Tribe's territory and the number of tribal members attending courses. | Academic Affairs/Student Affairs/ President's Office
North Country CC - Workforce Development Partnership
[5 empty] | 3Di. Assess need for a point-person to lead Continuing Ed (CE), Workforce Development (WFD) and Career and Technical Education (CTE) area permanently. | Conduct assessment of need for dedicated individual to lead CE, WFD and CTE area of the college. | If found viable, develop proposal for CE/WFD/CTE Coordinator | Permanently-funded position to lead Continuing Ed, Workforce Development and CTE areas Develop and deliver more specific and aggressive workforce development programming | Administration/Academic Affairs/HR
[5 empty] | 3Dii. Continue to host North Country CC-Workforce Development (NCCC-WFD) Partnership with county, tribal and regional workforce representatives, identifying employment needs | In addition to the regular meeting and information sharing forum, explore 1-2 workforce opportunities/initiatives that we could work on together. If determined feasible, map out plan for addressing those opportunities, including expected outcomes. | Continue with regular meeting and information sharing forum. If WFD plan developed, participate in the role assigned. | Be resource for county economic development and regional/tribal workforce partners to help unemployed reskill/prepare for new careers Serve as partner with county economic development partners in helping to attract new businesses/employers. | President's Office/Academic Affairs/CTE Coordinator/Enrollment
[5 empty] | 3Diii. Increase partnerships with area employers and identify business training and continuing education needs that the college can provide (e.g. IP, St. Joe’s, Mtn Lakes, Elderwood) | Conduct outreach to areas businesses to identify business training and continuing education needs. | Tailor needs of business and create courses/ programs to meet those needs. Create modular components that add up to credits - Identify courses that are easily modularized - Align credits with industry standards Market collaborative efforts through press releases | Expanded use of College resources to assist area employers with their business needs. | Academic Affairs
"Right-size" College operations to enrollment/ finance and work smarter improving efficiencies across functional areas
[5 empty] | 4Ai. Program analysis and realignment to fit within workforce needs and student desires | See 1Ci above | See 1Ci above | See 1Ci above
[5 empty] | 4Aii. Identify additional operational efficiencies leading to reduced costs | Complete similar analysis of other administrative and support operations | Develop proposal(s) that map out new, more efficient processes | Improved efficiencies, increased job satisfaction and corresponding reduction in labor costs by finding new, more effective ways to work, especially on manual and paper-dependent processes.
[6 empty] | Identify operations/processes that can be streamlined or made more efficient | Work with area supervisors and appropriate CBAs to define/change positions and position descriptions
[6 empty] | Evaluate manual tasks that could be successfully automated | Implement new processes and assignments and assess
[5 empty] | 4Aiii. Analysis of administrative, campus and support operations leading to increased efficiencies | Complete similar analysis of other administrative and academic support operations including branch campuses | Work with area supervisors and appropriate CBAs to define/change positions and position descriptions Undertake newfound patterns and efficiencies and assess for effectiveness and realizing cost-saving. | Determine areas for cost-saving and efficiencies across facilities | Administration/Academic Affairs/CFO/Enrollment/HR/Student Affairs
[6 empty] | Within each administrative department, identify the work they are responsible for and identify any gaps, redundancies, or opportunities for improvement. Within each administrative department, assess the skills and aptitudes of each employee and evaluate their fit for the work responsibilities therein. Within each administrative department, identify optimum staffing pattern needed to carry out mission and meet operational and strategic needs. | Assess costs to operate each campus and identify efficiencies and reimagined use of campuses/space Explore alternative use of space with partners including county(ies)
[5 empty] | 4Aiv. Explore more cost-effective solutions related to printing | Identify current unrecovered/costs associated with printing and, if possible, tease out costs associated with larger-scale print jobs | Present set of alternatives to campus community for consideration and adoption. Include in plan ways to control costs to the institution as well as waste | Thorough review of the problem, creation of alternatives and adoption of some high-value, high-impact practices that can be assessed later. | IT/Task Force
[6 empty] | Convene a representative task force to identify current issues and challenges associated with large-scale printing - costs, sustainability, revenue loss Explore pedagogical/learning value of printed material for student-learning | Adoption of some of the most high-value, high-impact recommendations to reduce printing costs while maintaining quality of student learning and operations
Identify alternatives/options to reduce printing costs while retaining access to printed work (e.g. large projects bundled, printed, packaged in more cost-effective way) Explore SUNY efforts in reducing printing costs and evaluate value of adopting at NCCC
Reconfigure organizational structure - faculty and staff size matches instructional, operational and strategic needs
[5 empty] | 4Bi. Develop and map out College Navigator/ Onboarding restructuring proposal | See 2Ai above | See 2Ai above | See 2Ai above | Administration/Academic Affairs/Enrollment/HR/Student Affairs
[5 empty] | 4Bii. Create more nimble staffing pattern, leveraging strengths and contribute talents in new ways | See 1Aiii and 4Aiii above | See 1Aiii and 4Aiii above | See 1Aiii and 4Aiii above | Administration/Academic Affairs/CFO/Enrollment/HR/Student Affairs
Develop prior learning assessment framework and process
[5 empty] | 4Ci. Assess cost-benefits of adopting prior learning assessment framework for students and college | Create prior learning assessment task force to research best-practices of prior learning assessments (PLAs) | If found to be positive, draft plan, process and policy, engaging academic and other departments and shared governance | Determine whether adopting PLA is in best of interest of students and college. | Academic Affairs/Enrollment/CFO
[5 empty] | 4Cii. If feasible, develop prior learning assessment implementation plan, process and policy. | Work with SUNY colleagues to identify and adopt/ develop a prior learning assessment tool Adopt tool and test it for accuracy Establish responsibilities for assessing and awarding credits for prior learning. Develop business plan for PLA including costs-to-college and costs-to-student to establish a fair and equitable cost structure. | Roll out the PLA process, assess, and make decisions on how to improve (or not) | If feasible, launch a prior learning assessment process. | Academic Affairs/Enrollment/CFO
New revenue streams to support mission and student experience
[5 empty] | 4Di. Partner with NCCC Foundation and NCCC Association to develop strategies to diversify funding to support mission of the College. | Meet with the NCCC Foundation and NCCC Association's Board(s) and present the College's interest in working jointly with the Association and Foundation in developing strategies to diversity funding streams to support students and the College mission and operations. Establish a small joint working group to map out a set of working principles, funding goals, methods, messaging, and actions, both collective and independent, that each entity can undertake. Present these to each entity's Board and seek endorsement of plan. | Have the working group transition to support the Foundation, Association, and College's efforts at scheduling and executing elements the plan. Establish funding targets, benchmarks and initiatives. Develop a calendar of events (both smaller, one-on-one, larger gatherings) to showcase the College and build interest in financially supporting our mission and students. | Develop alternative funding strategies aligned with College mission that help protect and expand the College's financial resources. | Administration
[5 empty] | 4Dii. Assess need and funding to support grant writer position. | Clarify operations or initiatives that we need grant support for. Reach out to SUNY CC and other colleagues regarding their experience with grant writers and value-added (or not). | If supported, hire grant writer (FT/PT) including exploring options to contract with local grant writers Apply for grants to support operations or new initiatives | Receive and manage new grants that support operations, advance college and lead to sustainable, improved practices. | Administration
[5 empty] | 4Diii. Explore opportunities to strengthen the Board of Trustees and the Foundation Board in their fundraising capacities, including collaborative fundraising efforts. | See 4Di above Schedule 1-2 joint meet-and-greets between the NCCC Foundation and the NCCC Board of Trustees to establish working relationships. Identify needs, training and otherwise, to strengthen fundraising skills of the Board of Trustees and Foundation Board. | See 4Di above Establish working group composed of the Board of Trustees, the NCCC Foundation Board and members of the administration to set up calendar of events focused on fundraising. | Develop vision and fundraising plan which contributes to the long-term operational health of the College. | Foundation Director/Association Director/Board of Trustees/Administration
* Assessment of Progress: Determine schedule for doing so

## Status Updates
August 23, 2021
Priority | Rationale | Planned Start | Status | Status Notes | Date Started | Date Completed | Principle Strategy | Initiatives | Strategic Actions/Tactics - 1st Year | Strategic Actions/Tactics - 2nd Year | Expected Outcomes | Primary Lead(s) | Administrative Supports | Academic Supports | Business Office/Bursar | Enrollment | Facilities | Financial Aid | IT/IR | Human Resources | Student Affairs | Budget | Assessment of Progress*
[5 empty] | In cases, there are not particular dates when actions were started |  | Faculty and Staff Professional Development
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | Pending start | Add faculty IT onboarding to this; Sarah has drafted an outlne to this; will begin with new hires for Fall 2021. |  |  |  | 1Ai. New Faculty Training Program | Identify necessary elements to orient new faculty members in regards to the College's educational philosophy; its mission, vision, values; pedagogical supports, course/syllabus development, and assessment of student learning outcomes | Launch new faculty training program, assess impact, and make changes as appropriate. | Establish effective onboarding and training program to equip new full-time and part-time faculty members with academic/instructional tools to more effectively teach. | Academic Affairs/Human Resources | Identify budget and human resources to establish training program. |  | NA | NA | Consult with with AA to ensure sufficient working areas/offices to support new faculty. | NA | Add faculty IT onboarding to this; | Will deliver universal onboarding elements and defer specifics to department/ | Add module related to reporting student misconduct, academic integrity violations; Add Title IX training to this…and diversity training | None
|  | Year 1 (2020-2021) | Pending start | [5 empty] | Create a template of a program (e.g. checklist) with corresponding supports (e.g. pre-recorded videos) to help deliver these
|  | Year 1 (2020-2021) | Pending start | [5 empty] | Identify onboarding needs of new faculty members beyond the academic area including onboarding, benefits, mandatory trainings | Launch new faculty training program, assess impact, and make changes as appropriate. | Ensure new full-time and part-time faculty members have a comprehensive understanding of benefits and training expectations.
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Universal design |  |  |  | 1Aii. Ongoing Professional Development | Identify faculty members to the lead adoption of and subsequent training in teaching modalities including high-flex | Expand opportunities to include College Bridge instructors. | Expanded use of professional development opportunities to improve teaching and/or develop new competencies which can enhance existing or create new program options | Academic Affairs/Human Resources | Dedicate funding to professional development. Working with academic departments, identify strategic PD needs. | ADA/504 needs at it applies to new teaching modalities; consider broader professional development trainings on improving accessible documents and courses | NA | NA | NA | NA | High-flex training of equipment use | NA | NA
|  | Year 1 (2020-2021) | [6 empty] | Resource professional development opportunities for teaching modalities, including high-flex, enabling training to take place
|  | Year 1 (2020-2021) | In-progress | Diverse Learners series with Landmark College (April 15-23, 2021) |  |  |  |  | Identify critical areas of professional development in pedagogy, both technological and behavioral | Develop training calendar and other opportunities for specific and universal professional development. Expand opportunities to include College Bridge instructors. |  |  |  | ADA/504 needs at it applies to new teaching modalities; consider broader professional development trainings on improving accessible documents and courses | [6 empty] | Be sure to include broader discussion around accommdative services in new modality;
Secondary | Important but not mission-critical; defer for year 1 |  | In-progress | Does this include the remote working agreement? If so, that is year 1 step. Does review of chairs and directors and their roles and compensation fit here? How does this fit within overload structure? |  |  | return to this item | 1Aiii. Faculty and Staff Positions and Patterns | Identify areas where increased flexibility in faculty and staff are possible to advance the mission (e.g. faculty in recruitment roles; faculty ambassadors to K-12; new program development release time) | Create greater flexibility in faculty and staff position descriptions to allow for flex into new areas (e.g. faculty into recruitment roles) | Creation of a more nimble faculty and staff able to leverage strengths and contribute talents in new areas/ways. | Academic Affairs/Human Resources | Develop proposals, share with collective bargaining units, gather input from President's Council and others. | Academic department chairs | NA | Desire for more generalist capabilities | Work with Academic Affairs on need for traveling faculty office spaces, adjunct faculty office spaces and full-time faculty office spaces in post-COVID-19 world. Plan and ready facilities to support these changes |  |  | Assist with negotiating | Desire for more generalist capabilities
| Requires other actions first; defer for year 1 |  | In-progress | Begun for Fall 2021; will be partially determined by student demand for online |  |  |  |  | Assess need for/changes to staffing pattern in post-COVID-19 world including number of traveling faculty members, online offices, | Negotiate with our collective bargaining units (CBUs) on new staffing patterns, work expectations, and position descriptions to better prepare for post-COVID-19 world | Develop expectations for a new working environment allowing for extended remote work and instruction. | Academic Affairs/Human Resources | Negotiate with CBUs
Secondary | Important but not mission-critical; defer for year 1 | Year 2 (2021-2022) |  | Climate assessment will help inform our weaknesses. Expected to be launched in Fall 2021. |  |  |  | 1Aiv.Commitment to Diversity, Equity, and Inclusion | See 2 Ci Conduct climate assessment and use results to develop actions to improve climate | See 2 Ci | Establish regular cycle of climate assessment and use of results to improve campus climate | Student Affairs/Academic Affairs
| Requires other actions first; defer for year 1 | Year 2 (2021-2022) |  | Might inclusion of diversity and accessibilty considerations as part of program review and course outline proposals help institutionalize this? Begin process in Fall 2021 |  |  |  |  | Conduct accessibility assessment and use results to develop actions to improve climate |  | Establish regular cycle of accessibility assessment and use of results to improve campus climate
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Common read is underway. First College-wide forum taking place this fall. Not certain that this will be a required reading in the course per Kate Wells. If stay with element, we'll need to choose a book that will easily apply. |  |  |  |  | Develop and adopt Common Read, integrated into First-Year Seminar
New Academic Programs and Certificates
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Program approved; recruitment, PLA, launch, and non-credit still outstanding. Currently marketed as part of the Business programs; there is a budget set aside for new programs… Other marketing opportunities to BOCES and beyond including WFD…all available online and aidable. Create trigger for to move toward launch once program approved...Requires a 60-day window to develop launch |  |  |  | 1Bi. Entre Cert | Register program with NYSED via SUNY Prepare for recruitment of new students Upon approval, launch recruitment efforts including marketing to area BOCES | Launch program and assess Identify non-credit opportunities Identify prior learning assessment credits that can be awarded (linked to experience) | Year 1 Recruitment = 10 students Year 2 Recruitment = 15 students | Academic Affairs/Academic Departments/Enrollment | College Navigator Restructuring | Ensure tutoring resources are available for new content area Assess for unique ADA/504 needs |  | Assess student interest/demand Assist with articulation possibilities |  | Assist with ensuring financial aid process between two institutions is seamless | Work with department regarding new/enhanced IT needs support integration of student grades from one SUNY institution to NCCC | Possible need for part-time faculty member |  | Insert costs….
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Health care admin track is part of AS Business program. Approved by SUNY and awaiting approval from NYSED |  |  |  | 1Bii. Health Care Admin | Register program with NYSED via SUNY Secure faculty member to teach new courses Prepare for recruitment of new students Upon approval, launch recruitment efforts including with area BOCES and health care organizations | Formalize articulation agreement with SUNY Canton Explore options for dual-marketing with SUNY Canton | Year 1 Enrollment = 10 students Year 2 Enrollment = 15 students | Academic Affairs/Academic Departments/Enrollment |  | Ensure tutoring resources are available for new content area Assess for unique ADA/504 needs
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) | In-progress | Discussions, both with internal and external groups, have yet to identify this program as in high demand in region. Similarly, it does not fit/align well with existing departmental structure. Awaiting departmental approvals |  |  |  | 1Biii. Cybersecurity | Determine demand, interest and capacity to deliver within mission Develop program aligned with Herkimer CC program Jointly work with BUS/CRJ to develop program Work with Herkimer CC to jointly register program Create program budget Move through NCCC shared governance process | Register program with NYSED via SUNY Secure faculty member to teach new courses Prepare for recruitment of new students Upon approval, launch recruitment efforts | Year 1 Enrollment = 10 students Year 2 Enrollment = 15 students | Academic Affairs/Academic Departments/Enrollment |  | Ensure tutoring resources are available for new content area Assess for unique ADA/504 needs |  |  | Possible configuration of new classroom
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) | In-progress | Awaiting departmental approval. Pick-up in Fall 2021 |  |  |  | 1Biv.Teaching Assistant Certificate | Determine demand, interest and capacity to deliver within mission Jointly work with HUM/SS Depts to develop program Create program budget Move through NCCC shared governance process | Register program with NYSED via SUNY Secure faculty member to teach new courses Prepare for recruitment of new students Upon approval, launch recruitment efforts | Launch affordable and desirable teaching assistant certificate as evidenced by enrollment Year 1 Enrollment = 10 students Year 2 Enrollment = 15 students | Academic Affairs/Academic Departments/Enrollment |  | Ensure tutoring resources are available for new content area Assess for unique ADA/504 needs
[8 empty] | Other Potential New Programs | Evaluate Labor Markets and Create Certificate Programs Based on Needs
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Focus here is on non-credit Basic Operations course. Challenge is finding qualified instructors |  |  |  | 1Bv. Wastewater Operator | see 1Biv. | see 1Biv. | Explore options of adding wastewater operator coursework, track or program linked to Envir Sci/Env Studies | Academic Affairs/Academic Departments/Enrollment |  |  |  |  | Possible configuration of new classroom
Tertiary | Requires other actions first; defer for year 1 | Year 3 (2022-2023) | Deferred | Requires master plan amendment, faculty hires |  |  |  | 1Bvii. Green Technologies | see 1Biv. | see 1Biv. | Assess need and ability to offer green technologies programs. | Academic Affairs/Academic Departments/Enrollment
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) | In-progress | Awaiting feedback from Childcare Coordinating Council Inc of Clinton County to identify courses that fit into child development associate certificate allowing folks to work and earn degree simultaneously Linked to PLA and/or development of professional portfolio 12 credit concentration that could fold into Teaching Assistantship to AA Lib Arts - Early Childhood |  |  |  | 1Bviii. Childcare | see 1Biv. | see 1Biv. | Explore options of adding childcare certificate with Human Services | Academic Affairs/Academic Departments/Enrollment
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) | In-progress | These have begun to take on greater import as the need for health care workers in the region grows Currently review Surg Tech and Med Tech Look for connections with OWS Rural Health Grant |  |  |  | 1Bix. Other Healthcare (Public Health; Surgical Tech, Medical Office Asst, CNA pathways) | see 1Biv. | see 1Biv. | Explore options of adding AS Public Health with Health Science | Academic Affairs/Academic Departments/Enrollment
Tertiary | Requires other actions first; defer for year 1 | Year 3 (2022-2023) | Deferred | Need master plan amendment Possible aid for non-credit |  |  |  | 1Bx. AOS Programs | see 1Biv. | see 1Biv. | Assess need and ability to offer AOS programs. | Academic Affairs/Academic Departments/Enrollment
Enhancing Existing Programs and Certificates
Secondary | Important but not mission-critical; defer for year 1 | Year 2 (2021-2022) |  | Review and revise program analysis tool; currently laying groundwork to assist with for next year; plan to begin analysis in Fall 2021; consider hiring 3rd party to provide objectivity and professional experience (Sarah will query listserve and Erik will ask CCBOA) |  |  |  | 1Ci. Program analysis and realignment to fit within workforce needs and student desires - grounded in data | Create alternate/standardized metric for economic analysis of programs to maximize resources and align revenue/expenditures links to mission, and value added to counties | Increase enrollment capacity of selective programs | A standardized tool to evaluate program health | Administration/Academic Affairs/Academic Departments
[9 empty] | Evaluate whether program(s) are mission-critical | Deactivate under-enrolled programs | A standardized and transparent process leading to deactivation/discontinuance of programs
|  |  |  | Revisit tool to evaluate programs; |  |  |  |  | Evaluate costs per: student/program/campus and overall costs/benefits | Where feasible, consolidate programs and leverage online environment to build capacity (e.g. AAS Computer Graphics on two campuses to one) | Reduction of under-enrolled sections and programs | Administration/Academic Affairs/Academic Departments
[9 empty] | Identify loss-leaders and profit-generators and focus on those growing and with stable enrollment | Adjust faculty/staff size relative to programs | Strengthened programs | Administration/Academic Affairs/IR
Follow up with identified programs and how to move forward with timelines
[9 empty] | Identify need for in-demand trades that align with existing certificates | Certificate programs: align in-demand trades with quickly completed certificates | Development of new or revitalized certificate programs linked to in-demand trades | Academic Affairs/Academic Departments/Enrollment
Secondary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Currently underway with CTE Coordinator position; planned o ramp up; Looking at using Cert of Health Science as a jumping off place to other careers... Surgical Tech; Med Tech; CNA to PN programs; Med Assistant; partner with Workforce Partners |  |  |  | 1Bii. Reinvest in health careers and health science programs where a) workforce needs exist, b) student desires exist, and c) our capacity to instruct or recruit faculty exist | Explore increasing clinical capacity and training opportunities in existing health care programs: needs assessment, student demand, cost/benefit analysis | Depending on year 1 findings, either move towards expanding existing health care enrollments or take no further action | Determine need and opportunity to expand existing health care programs. | Administration/Academic Affairs/Enrollment |  |  |  |  | Work with Academic Affairs, Nursing Dept and Health Sciences on plan to update nursing labs
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 2 (2021-2022) | In-progress | Initial steps include standardized data needs for all academic programs as part of ongoing program assessment; provided to program directors with goal of creating dashboards with updated information quarterly |  |  |  | 1Biii. Focus on data-driven decision-making with improved IR functionality | Develop weekly IR reporting dashboards | Identify external data sources to determine student interest in programs and in-demand career paths | Improved access to data | IR/Administration/Academic Affairs/Enrollment
|  |  |  | Consider separating IT from IR? Erik noted that IT should be protecting the integrity and others use the database to access the data; explore adoption of better database (e.g. Tableau?) |  |  |  |  | Better resource (funding and staff) and increase access to institutional research data | With assistance from IR, evaluate new staffing pattern and assess effectiveness for student and faculty/staff support. | Increased numbers of trained staff on use of data reporting tools | IR/Administration/HR
|  |  |  | Other schools have advancement and IR responsibilities |  |  |  |  | Use data for decision making in assessment of programs, program review, grant applications, marketing and enrollment efforts |  | Timely and more readily accessible data sources | IR/Administration
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Program-specific marketing campaigns; traditional and non-traditional marketing techniques; current campaigns will help assess student/ regional demand |  |  |  | 1Biv. Increase enrollment in existing programs where student interest and regional demand exist | Identify additional ways to effectively market current programs in our local communities. | Assess novel marketing strategies for those programs identified | Increased interest and enrollment in targeted programs using novel marketing strategies, or, find evidence that programs have lost market interest and use information to either refresh or deactivate program(s) | Enrollment |  |  |  |  | Work with AA and IT to identify and update classrooms on each campus to support high-flex teaching needs. | [5 empty] | include SUNY BI review of system-wide enrollment and include it in the program analysis
|  | Year 1 (2020-2021) | In-progress | Program-specific marketing campaigns; traditional and non-traditional marketing techniques; current campaigns will help assess student/ regional demand |  |  |  |  | Identify 4-5 programs to market where student interest and regional demand exist | Use lessons learned from prior year to improve marketing strategies of existing programs |  | Enrollment/Academic Affairs |  |  |  |  | Develop alternative facilties plan to address smaller budget facilities upgrades that position the campus gradually and continuously improve facilities in absence of significant funding from sponsors.
|  | Year 1 (2020-2021) | In-progress | Program-specific marketing campaigns; traditional and non-traditional marketing techniques |  |  |  |  | Develop 2-3 new strategies to market current programs in our service area |  |  | Enrollment
|  |  |  | Is there a way to gain enrollment regionally by improving employee skill set? Tap into union contracts to assist with employee PD. Whose responsibility? - Joe take on at the DOCCS/FCI level. - Jeff Tedford at DOCCS and ??? At FCI |  |  |  |  | Reach out to Labor Unions such as NYSCOBA and Federal CO unions to Partner and Offer Certificates/Degrees to Employees | Development of select pathways for regional employers staff to academic programs and certificates | Assess needs of regional employers and, where needs exist, develop select pathways for individuals to existing programs. | Academic Affairs/Enrollment
|  |  |  | Objectives for program advisory and campus advisory boards; WFD Partnership; CTE Coordinator; Perkins CLNA Sarah noted federal and state funding in area of internships and beyond. How to integrate these? |  |  |  |  | Determine needs of these regional employers and work with respective departments to develop pathways for these individuals |  |  | Academic Affairs/Enrollment
Secondary | Important but not mission-critical; defer for year 1 | Year 2 (2021-2022) | Deferred | Remote work proposal positions us to pivot in this direction if need are there; 21-22 year will also reveal whether there is demand for some programs to move to online (e.g. Business/HUS) |  |  |  | 1Bv. Expansion of low-residency programs | Assess Spring 20, Fall 20 and Spring 21 data for student interest and performance in low-residency programs | If determined feasible, seek out any approvals required and launch new low-residency delivery of existing programs. | Determine demand, capacity and opportunity to deliver low-residency programs in cost-effective ways and, where feasible, launch them. | Academic Affairs/IR/Academic Departments
|  |  |  | Do we need to shift from "low residency" to "remote/hybrid" - Seems like it emerged from Summer 20 strategic plan; Data sources could include SUNY and NCCC student surveys; creating focus groups prospectively; examine student performance data for trends (by program; by discipline; by course) Are there other external data point (e.g. ACT) that could give us insight into this? Is there a model from other institutitions that we could use? |  |  |  |  | Work with appropriate departments to develop selective new low-residency options where demand, interest and capacity to deliver intersect | If feasible, work with departments to prepare for marketing and launch of new programs. | Effective marketing and subsequent enrollment and launch of new programs. | Academic Affairs/IR/Academic Departments/Enrollment
[9 empty] | Determine if there are any required additional approvals from NYSED or MSCHE |  |  | Academic Affairs
Facilities to Support New and Enhanced Programs
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Contract signed; site work slated to begin; installation planned for July 202 | 2021-03-26 |  |  | 1Di. Create 1-2 state-of-the-art classrooms to support high-flex model of teaching and learning | Designate 1-2 classrooms on each campus to be upgraded to support high-flex teaching and learning | Designate 1-2 classrooms on each campus to be upgraded to support high-flex teaching and learning | Development of two classrooms on each campus to support high-flex teaching and learning. | Facilities/Academic Affairs |  |  |  |  | Work with AA and IT to identify and update classrooms on each campus to support high-flex teaching needs.
|  |  | In-progress | Identified - HEERF |  |  |  |  | Identify initial financial resources to support upgrade including evaluating for capital reimbursement. | Develop plan for sustainability of these classrooms and consider expansion | Link these investments to plan for upgrading and standardization of instructional technology across the college and to capital facilities planning. | [5 empty] | Develop alternative facilties plan to address smaller budget facilities upgrades that position the campus gradually and continuously improve facilities in absence of significant funding from sponsors.
|  |  | In-progress | Done | 2021-03-26 |  |  |  | Gather input from faculty, IT, and others on rooms, design elements to inform plan | Gather input from faculty, IT, and others on rooms, design elements to inform plan
|  |  |  | Five (5) slated - 2 in ML, 2 in SL, 1 in TI |  |  |  |  | Upgrade at least one (1) room on each campus. | Using learning from year one, upgrade at least one (1) additional classroom on each campus
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Application for Community Project Funding through Rep Stefanik, Sen Schumer, and Sen Gillibrand If not funded, reach out to state reps for SAM funding |  |  |  | 1Dii. Work with Nursing Department to modernize Nursing Labs on all three campuses | Identify most creative means to modernize existing lab space to best support clinical teaching and learning for PN and ADN students | Upgrade at least one (1) lab over the summer and use faculty and student input to inform next round. If possible, make second upgrade over winter break and third during the upcoming summer break. | Development of two updated, state-of-the-art clinical simulation labs that support student learning and success in clinical setting and when placed in workforce. | Facilities/Academic Affairs |  |  |  |  | Work with Academic Affairs, Nursing Dept and Health Sciences on plan to update nursing labs
|  |  | In-progress | [5 empty] | Identify particular needs (e.g. simulation) and include planned headwall simulators as part of project
|  |  | In-progress | [5 empty] | Develop budget and sources of financing to support project | Identify how best to sustain upgrades and plan for future ones. | Development of a plan, linked to Nursing program review, evaluating labs and identifying resources to keep them operating effectively.
|  |  | In-progress | [5 empty] | Develop priority plan for which campus to modernize first | Use learnings from prior year's modernization efforts to inform this years.
Student Success Initiatives
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | NC Navigator has been deployed since April 2021; phase 1-3 underway; moving onto phase 4-6 until Sept; aligned student self-service with communications and support |  | Resume here | These are linked to and we'll want to reference to Retention/ Completion/ Placement | 2Ai. Develop and map out North Country Navigator/ Onboarding restructuring proposal. | Work with various areas and supervisors to identify the existing flow of student onboarding, from application to first week of classes. Use input to improve student experience and help them be better prepared to start classes. Identify new operational efficiencies and work with CBAs and employees to restructure positions/work to better serve students. | Launch Navigator/Onboarding proposal. | Restructure administrative and student support positions, creating student college navigators leading to improved supports for and preparation of students as they begin or return to college. Improved persistence, retention and completion rates of students as students are better equipped to engage tools for success. Improved delineation of processing tasks leading to improved efficiencies in data-processing. Improved satisfaction among employees as operational inefficiencies are reduced, positions become better calibrated to changing technological conditions (e.g. reduction in processing needs), and employees are encouraged to develop and build more skills | Administration/Academic Affairs/Enrollment/HR/Student Affairs
Secondary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | program landing pages set up with new template; next step will be to include most current advising materials and degree plan pages; New template for degree plan pages underway |  |  |  | 2Aii. Improved advising resources to help students be better informed and plan for their future | Advisement Committee will review and identify additional gaps in advising resources Advisement Committee will recommend changes and improvements in program webpages and college catalog. Integrate course catalog with academic program pages, creating a more dynamic and user-friendly experience for students to access and reference. | Review and refine advising resources. Develop degree plan pages including program course sequences Develop a process for ongoing updates prior to each new academic year. | Improved understanding by students of possibilities and pathways associated with various fields of study. Modest improvement in completion by students as they will have a more informed sense of and commitment to their academic choices. | Academic Affairs/Advisement Committee
Secondary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Certificate group formed to address; |  |  |  | 2Aiii. Develop infographics for students to use to visualize academic pathways to careers and transfer opportunities. | CTE Coordinator to lead task force of faculty and enrollment staff to identify 3-4 CTE pathways to focus on based on student interest and demand. Develop a template to map out visual pathways for career and transfer opportunities withing those programs. Gather input from full faculty and pilot use with newly recruited and first year students. | Based on input from students, faculty, and staff modify the template as need be. Expand model to all programs. Develop procedures to include annual review and update of the document, centrally located and easily accessible. | Improved understanding by students of possibilities and pathways associated with various fields of study. Modest reduction in time-to-completion by students as they will have a more informed sense of where their academic choices and take them. | CTE Coordinator/Academic Departments/VPAA/Student Affairs
Revitalized First-Year Seminar
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Currently 8 sections (online and F2F); seminar remains credit-bearing; course outline updated; created option of CSP 100 in worksheets under Health/PED |  |  |  | 2Bi. Replace and refresh CSP 100 College Success Seminar with more current and topical content and delivery | The LAC Coordinator for our Malone campus will convene a task force composed of faculty, academic support and student affairs employees to map out the particulars of a first-year seminar. That group will develop a proposal to include content, delivery methods/modalities, assessment measures and the like. If the seminar is credit-bearing, work with the various entities (academic departments, Curriculum Committee, College Senate) to obtain support to offer within programs, approval to include in curriculum, and assistance in recruiting students. If seminar is not credit-bearing, determine how students will be recruited to the course and how the costs will be offset. | Launch updated First-Year Seminar. Informally assess delivery and student engagement throughout the semester. Formally assess student performance at semester's end. Make any recommended changes based off of first semester and offer again in spring term. | Improved student persistence, retention, and completion as students will be better prepared and/or improve their technological, behavioral and cognitive skills to meet the demands of a college education. Increased enrollment in and satisfaction with the course by students. | LAC Coordinator - Malone Campus/First-Year Seminar Task Force/Academic Affairs
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) | Deferred | some discussion underway; will need to align Common Read selection for Fall 2022; re-evaluate having Common Read as part of FYS |  |  |  | 2Bii. Common Read integration into First-Year Seminar | See 2Di below | Take learnings from Common Read experience and fold into First-Year Seminar. | Expanded
College-wide Diversity Commitments
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) | Deferred | In holding pattern because SUNY is working on an assessment tool; also problems with what constitutes "climate" assessment… |  |  |  | 2Ci. Regular Climate Assessment | See 1Aiv Identify a climate assessment instrument to be used. This is currently being explored with the student affairs group within the SUNY community college sector. Identify budget line to support adoption of said plan if needed. Set up plan to administer the assessment for 2021-22 year and establish a sustainable cycle of ongoing administration. If possible, align cycle opposite Student Opinion Survey administration. | See 1Aiv Administer survey and analyze survey results. Mine results to identify areas needing attention and resources, leading to development of initiatives to address needs. | See 1Aiv Long-term: development of an ongoing cycle of climate assessment and use results for continuous improvement in realizing diversity commitments and goals. Short-term: deliver and analyze survey, using results to inform changes. | Student Affairs
Primary | Important but not mission-critical; defer for year 1 | Year 1 (2020-2021) | Completed | The policy, "Name Change Policy" was passed by BoT on Feb 26, 21; Kim has created a checklist to work with IT and Records to assure implementation; Tara will fold into HR operations as well; |  |  |  | 2Cii. Preferred Name Policy | Continue movement of policy through shared governance system, including student input. Present the policy to the administration and Board of Trustees for approval. | Adopt and implement policy and make adjustments to its operations as issues arise. | Students would be able to identify and present themselves within our community by their preferred name. | Student Affairs/Registrar
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) |  | Consider contracting with external providers to conduct access assessment; inquire with Cammy |  |  |  | 2Ciii. Accessibility Assessment | Recruit a small interdisciplinary task-force to conduct an accessibility assessment of physical and electronic/digital locations. Identify instrument and process for conducting said assessment. Identify budget and other resources needed to conduct assessment. | Conduct assessment and analyze results by campus and by building/location (including digital/electronic). Identify high-priority items to place attention and resources to. Develop plan to address those needs and for continuing to assess and improve accessibility. | Establish an accessibility baseline and plan to continuously assess and improve. Improve accessibility to physical locations and buildings as well as electronic/digital resources (i.e. website, library, course materials). | Student Affairs/Academic Affairs/ADA-504 Coordinator/Facilities
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) | Deferred | Do we want to include reference to SUNY Gen Ed changes? |  |  |  | 2Civ. Explore inclusion of diversity commitment as part of program review. | Develop list of diversity commitments with illustrations of where they are currently being expressed and possibilities to do so in other areas. Conduct college-wide town hall meeting to explore possibilities of institutionalizing diversity commitments by including them as part of program review, academic and other. Request academic and other departments to consider and provide input on how this may be work within their program review cycles. | Identify or develop a rubric for how diversity commitments can be folded into program activities/plans/operations. Adopt a rubric for how diversity commitments can be assessed within program review. Work with individual departments to test the instruments and report out findings. | Assess institutional interest in broadening assessment of diversity commitment into program review. Use findings to improve carrying out diversity commitments. | Student Affairs/Academic Affairs
Expand integrated diversity-focused programming and services
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress |  |  |  |  | 2Di. Common Read. | Led by the Interim VP for Student Affairs, the College's Diversity Task Force will select a common read and will encourage faculty and departments to find ways to integrate it into their courses/operations. Engage key college structure/leader (e.g. President's Council) to begin the process and discuss as a unit. Move Common Read out to faculty and staff more broadly and create corresponding times to delve more deeply into the topics under consideration and identify what, if any, changes we can consider. | Assess the impact and perceived value of the common read for the faculty and staff. Explore recommended changes to our operations in regards to strengthening our ability to engage, support and improve upon our commitments to diversity across the college. Use these assessments to plan for and improve the process for the next year, if found valuable. | Increased appreciation by the college community on the value of an integrated and focused set of diversity-related activities and services. Specially for the common read, an improved understanding a diverse perspective which leads to more compassion for and towards those of different backgrounds who work and study at the College. Increase cultural competency among workforce and student body. Gain ability to recognize inequities and implicit biases that may be present in college operations and affect the student and workforce experience. | VP for Student Affairs/Diversity Task Force
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | are there other diversity-related programming that we are planning? |  |  |  | 2Dii. North Country Live - Continuing Education Series | Led by the Opportunities group and working in conjunction with Academic Affairs and Student Affairs, build upon the very successful series from Summer 20 (the African-American Experience in the Adirondacks), and Fall 2020 (the St. Regis Mohawk Tribe, past and present) | Need to add more here | Increased recognition and celebration of diversity in our communities. Provide diversity-related programming to our campus and the broader communities. | Opportunities Group/Student Affairs/Academic Affairs
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) | Deferred |  |  |  |  | 2Diii. Create and launch a self-paced diversity course for faculty and staff.
Expand K-12 and Higher Ed partnerships
Tertiary | Important but not mission-critical; defer for year 1 | Year 2 (2021-2022) | Deferred | Some exploration taking placing with PSC and Nicholas Hunt-Bull, Provost, on shared services with PSC. Most of the colleges noted are undergoing leadership changes. PSC Director of Development pledged to assist our new Foundation Director with Donor Search |  |  |  | 3Ai. Establish regional college consortiums with opportunities for shared services and cross-institutional enrollment | Set up initial meetings with Associated Colleges of St. Lawrence, PSC, Clinton CC, SUNY Plattsburgh, SUNY Empire | Explore opportunities to partner in areas where we or they have greater expertise or strengths including academic program collaborations, library services, shared services and cross-institutional enrollment | Establish regional college consortiums with opportunities for shared services and cross-institutional enrollment Explore merger possibilities (e.g. Clinton CC) if consortium agreements and shared services bear fruit | Administration/Academic Affairs
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) | Deferred | Concerns around available space to host other colleges. Most of the colleges noted are undergoing leadership changes. Recommend conducting a cost-benefit analysis. Sarah will reach out to John Jablonski to see what benefit they gain. |  |  |  | 3Aii. Development of co-location of 4-year institutions on campus and specific shared service agreements | Explore 4-year schools to our campus (on campus BA degrees though other schools) | If feasible, establish agreement and work towards establishing co-location of baccalaureate programs |  | Administration/Academic Affairs/Enrollment |  |  |  |  | Work with AA on the facilities needs should co-location of operations become viable.
Secondary |  | Year 1 (2020-2021) | In-progress | Cybersecurity currently at CRJ department for consideration. |  |  |  | Development of new program collaborations | Identify new program collaborations to better serve student interest and regional demand - Cybersecurity with Herkimer CC - Health Care Admin with SUNY Canton - ??? with Clinton CC | (see above under New Programs) | (see above under New Programs) | Administration/Academic Affairs/Enrollment
Secondary |  | Year 1 (2020-2021) | In-progress | Added three new articulation agreements in 2020-2021 (Aspen Univ; SUNY Canton; SUNY Upstate) Work with Bruce K on assessing status and current success in 2021-2022 |  |  |  | 3Aiii. Expanded 2+2 agreements, articulation agreements, and increased transfer opportunity for students. | Assess status and success of current articulation/2+2 agreements | Develop, update and expand articulations agreements, other partnerships and dual registration opportunities with regional colleges | Expanded 2+2 agreements, articulation agreements, and increased transfer opportunity for students. Establish a process for maintaining, tracking, and marketing those agreements to and for students | Student Affairs/Enrollment/Academic Affairs
Continuing Education - K-12 and Licensed Professionals
Secondary | Important but not mission-critical; defer for year 1 | Year 2 (2021-2022) | Deferred |  |  |  |  | 3Bi. Provide Continuing Education for Licensing Programs (healthcare, childcare, education) | Defer until year 2 | Assess needs for continuing education and college's ability to deliver in cost-effective, revenue enhancing way | Use assessment data to inform next steps. | Academic Affairs/CTE Coordinator
Secondary | Important but not mission-critical; defer for year 1 | Year 2 (2021-2022) | Deferred |  |  |  |  | 3Bii. Provide Continuing Education Programs for K-12 Teachers | Defer until year 2 | Assess needs for continuing education and college's ability to deliver in cost-effective, revenue enhancing way | Use assessment data to inform next steps. | Academic Affairs
Secondary |  | Year 1 (2020-2021) | In-progress | Kim D has begun, conducted needs assessment, and has begun to reach out to Malone business community | 2021-06-01 |  |  | 3Biii. Offer More Training Programs (i.e. Business Dept. current plan for offering professional skills training) | Assess needs for continuing education and college's ability to deliver in cost-effective, revenue enhancing way | Assess needs for continuing education and college's ability to deliver in cost-effective, revenue enhancing way | Use assessment data to inform next steps. | Academic Affairs/Departments
Expand Partnership with St. Regis Mohawk Tribe
Secondary | Requires other actions first; defer for year 1 | Year 1 (2020-2021) | In-progress | Certain steps are already being taken. Defer further action until pandemic eases and both parties are able to resume. Tribal members are serving on some program advisory boards, on WFD board, and campus advisory board. |  |  |  | 3Ci. Strengthen and nurture the working relationship with the St. Regis Mohawk Tribe (SRMT) including exploring other ways to support the academic and continuing educational needs of tribal members | Continue to invite SRMT representatives and members to participate in campus, program and college-wide advisory groups/boards. Identify areas of need, including workforce training, continuing education, and related areas where the College could be helpful. Explore opportunities for member of the SRMT to serve on the College Foundation Advisory Council. | Offer reciprocal willingness to assist and serve on advisory councils that would be helpful to the SRMT. Collaborate with SRMT WFD and College WFD to provide any training and continuing education where identified. Invite members of the SRMT to serve on the College Foundation Advisory Council. Invite a member of the SRMT to be a commencement speaker. | Be known as a college committed to the success of St. Regis Mohawk Tribal community as evidence by partnership and working relationship | Academic Affairs/Student Affairs/ President's Office
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | BUS 100 and ENG 101 slated to run in Fall 2021. Currently, human services and business programs is where the needs are. The pandemic disrupted operations and we are awaiting opportunity to return. Developing predictable schedule for folks based on need as the students who started with us have progress through campus on online courses |  |  |  | 3Cii. Working with St. Regis Mohawk Tribe's education partners, expand offerings that best serve student and tribal needs | Continue partnership with SRMT Education Department to identify course offerings, marketing, and recruitment of students. Assess course offerings, student performance, and student interest to inform the following year's schedule and supports. | Working with SRMT Education Department, expand offerings where student interest and college capacity align. Delivery courses, assess course offerings, student performance, and student interest to inform the following year's schedule and supports. | Increase the number of courses offered on the St. Regis Mohawk Tribe's territory and the number of tribal members attending courses. | Academic Affairs/Enrollment
North Country CC - Workforce Development Partnership
Secondary | Top priority; mission-critical; pre-requisite for other initatives | Year 2 (2021-2022) | Deferred | Currently funded through Perkins; funding in WFD is expected to continue to be bright; WF needs in counties helped by this; |  |  |  | 3Di. Assess need for a point-person to lead Continuing Ed (CE), Workforce Development (WFD) and Career and Technical Education (CTE) area permanently. | Conduct assessment of need for dedicated individual to lead CE, WFD and CTE area of the college. | If found viable, develop proposal for CE/WFD/CTE Coordinator | Permanently-funded position to lead Continuing Ed, Workforce Development and CTE areas Develop and deliver more specific and aggressive workforce development programming | Administration/Academic Affairs/HR
| Requires other actions first; defer for year 1 | [7 empty] | Assist with non-credit to credit conversion (prior-learning assessment) and develop non-credit options. Expecting to see additional funding for apprenticeship
Explore Center for Entrepreneurial Design and Research (CEDAR); - grant-funding to start-up through Senate earmarks;
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | In-progress | Hold on next meeting until start of the Fall 2021 semester.; Explore Education Opportunity Center in North Country - run by Sylvie Nelson. |  |  |  | 3Dii. Continue to host North Country CC-Workforce Development (NCCC-WFD) Partnership with county, tribal and regional workforce representatives, identifying employment needs | In addition to the regular meeting and information sharing forum, explore 1-2 workforce opportunities/initiatives that we could work on together. If determined feasible, map out plan for addressing those opportunities, including expected outcomes. | Continue with regular meeting and information sharing forum. If WFD plan developed, participate in the role assigned. | Be resource for county economic development and regional/tribal workforce partners to help unemployed reskill/prepare for new careers Serve as partner with county economic development partners in helping to attract new businesses/employers. | President's Office/Academic Affairs/CTE Coordinator/Enrollment
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) | Deferred | Seems to blend with others above. Related to 3Di. |  |  |  | 3Diii. Increase partnerships with area employers and identify business training and continuing education needs that the college can provide (e.g. IP, St. Joe’s, Mtn Lakes, Elderwood) | Conduct outreach to areas businesses to identify business training and continuing education needs. | Tailor needs of business and create courses/ programs to meet those needs. Create modular components that add up to credits - Identify courses that are easily modularized - Align credits with industry standards Market collaborative efforts through press releases | Expanded use of College resources to assist area employers with their business needs. | Academic Affairs
|  |  |  | Resume here |  |  | "Right-size" College operations to enrollment/ finance and work smarter improving efficiencies across functional areas
|  |  |  | See Common Ground Alliance notes. Selina and non-credit 600 hour financial aid with BOCES. Possible outcome of MSCHE self-study. Revisit in early October. |  |  |  | 4Ai. Program analysis and realignment to fit within workforce needs and student desires | See 1Ci above | See 1Ci above | See 1Ci above
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) |  | Continued automation and self-service that is underway will help with decreased costs for processing. Developing forms within Slate will continue to drive efficiencies. Roll-out planning in tandem and with fully community awareness after self-study. Empower departments/cross departmental team to make recommendations for improvements and cost-effectiveness. |  |  |  | 4Aii. Identify additional operational efficiencies leading to reduced costs | Complete similar analysis of other administrative and support operations | Develop proposal(s) that map out new, more efficient processes | Improved efficiencies, increased job satisfaction and corresponding reduction in labor costs by finding new, more effective ways to work, especially on manual and paper-dependent processes.
[9 empty] | Identify operations/processes that can be streamlined or made more efficient | Work with area supervisors and appropriate CBAs to define/change positions and position descriptions
[9 empty] | Evaluate manual tasks that could be successfully automated | Implement new processes and assignments and assess
Secondary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) |  | Empower departments/cross departmental team to make recommendations for improvements and cost-effectiveness. Find ways to include both internal (bird's-eye) view with external perspective similar to program review - consider external with athletics and career services |  |  |  | 4Aiii. Analysis of administrative, campus and support operations leading to increased efficiencies | Complete similar analysis of other administrative and academic support operations including branch campuses | Work with area supervisors and appropriate CBAs to define/change positions and position descriptions Undertake newfound patterns and efficiencies and assess for effectiveness and realizing cost-saving. | Determine areas for cost-saving and efficiencies across facilities | Administration/Academic Affairs/CFO/Enrollment/HR/Student Affairs
[9 empty] | Within each administrative department, identify the work they are responsible for and identify any gaps, redundancies, or opportunities for improvement. Within each administrative department, assess the skills and aptitudes of each employee and evaluate their fit for the work responsibilities therein. Within each administrative department, identify optimum staffing pattern needed to carry out mission and meet operational and strategic needs. | Assess costs to operate each campus and identify efficiencies and reimagined use of campuses/space Explore alternative use of space with partners including county(ies)
Tertiary | Requires other actions first; defer for year 1 | Year 2 (2021-2022) |  | Three considerations: 1) faculty printing for class/student handouts, 2) student printing of faculty materials/texts, 3) other professional staff/MC. Analysis of local faculty/staff printers and needs for (e.g. ADA/504 Coordinator). Start with printing costs by department/area/cost center |  |  |  | 4Aiv. Explore more cost-effective solutions related to printing | Identify current unrecovered/costs associated with printing and, if possible, tease out costs associated with larger-scale print jobs | Present set of alternatives to campus community for consideration and adoption. Include in plan ways to control costs to the institution as well as waste | Thorough review of the problem, creation of alternatives and adoption of some high-value, high-impact practices that can be assessed later. | IT/Task Force
[9 empty] | Convene a representative task force to identify current issues and challenges associated with large-scale printing - costs, sustainability, revenue loss Explore pedagogical/learning value of printed material for student-learning | Adoption of some of the most high-value, high-impact recommendations to reduce printing costs while maintaining quality of student learning and operations
Identify alternatives/options to reduce printing costs while retaining access to printed work (e.g. large projects bundled, printed, packaged in more cost-effective way) Explore SUNY efforts in reducing printing costs and evaluate value of adopting at NCCC
|  |  |  | resume here |  |  | Reconfigure organizational structure - faculty and staff size matches instructional, operational and strategic needs
[8 empty] | 4Bi. Develop and map out College Navigator/ Onboarding restructuring proposal | See 2Ai above | See 2Ai above | See 2Ai above | Administration/Academic Affairs/Enrollment/HR/Student Affairs
[8 empty] | 4Bii. Create more nimble staffing pattern, leveraging strengths and contribute talents in new ways | See 1Aiii and 4Aiii above | See 1Aiii and 4Aiii above | See 1Aiii and 4Aiii above | Administration/Academic Affairs/CFO/Enrollment/HR/Student Affairs
Develop prior learning assessment framework and process
[8 empty] | 4Ci. Assess cost-benefits of adopting prior learning assessment framework for students and college | Create prior learning assessment task force to research best-practices of prior learning assessments (PLAs) | If found to be positive, draft plan, process and policy, engaging academic and other departments and shared governance | Determine whether adopting PLA is in best of interest of students and college. | Academic Affairs/Enrollment/CFO
[8 empty] | 4Cii. If feasible, develop prior learning assessment implementation plan, process and policy. | Work with SUNY colleagues to identify and adopt/ develop a prior learning assessment tool Adopt tool and test it for accuracy Establish responsibilities for assessing and awarding credits for prior learning. Develop business plan for PLA including costs-to-college and costs-to-student to establish a fair and equitable cost structure. | Roll out the PLA process, assess, and make decisions on how to improve (or not) | If feasible, launch a prior learning assessment process. | Academic Affairs/Enrollment/CFO
New revenue streams to support mission and student experience
[8 empty] | 4Di. Partner with NCCC Foundation and NCCC Association to develop strategies to diversify funding to support mission of the College. | Meet with the NCCC Foundation and NCCC Association's Board(s) and present the College's interest in working jointly with the Association and Foundation in developing strategies to diversity funding streams to support students and the College mission and operations. Establish a small joint working group to map out a set of working principles, funding goals, methods, messaging, and actions, both collective and independent, that each entity can undertake. Present these to each entity's Board and seek endorsement of plan. | Have the working group transition to support the Foundation, Association, and College's efforts at scheduling and executing elements the plan. Establish funding targets, benchmarks and initiatives. Develop a calendar of events (both smaller, one-on-one, larger gatherings) to showcase the College and build interest in financially supporting our mission and students. | Develop alternative funding strategies aligned with College mission that help protect and expand the College's financial resources. | Administration
[8 empty] | 4Dii. Assess need and funding to support grant writer position. | Clarify operations or initiatives that we need grant support for. Reach out to SUNY CC and other colleagues regarding their experience with grant writers and value-added (or not). | If supported, hire grant writer (FT/PT) including exploring options to contract with local grant writers Apply for grants to support operations or new initiatives | Receive and manage new grants that support operations, advance college and lead to sustainable, improved practices. | Administration
[8 empty] | 4Diii. Explore opportunities to strengthen the Board of Trustees and the Foundation Board in their fundraising capacities, including collaborative fundraising efforts. | See 4Di above Schedule 1-2 joint meet-and-greets between the NCCC Foundation and the NCCC Board of Trustees to establish working relationships. Identify needs, training and otherwise, to strengthen fundraising skills of the Board of Trustees and Foundation Board. | See 4Di above Establish working group composed of the Board of Trustees, the NCCC Foundation Board and members of the administration to set up calendar of events focused on fundraising. | Develop vision and fundraising plan which contributes to the long-term operational health of the College. | Foundation Director/Association Director/Board of Trustees/Administration
* Assessment of Progress: Determine schedule for doing so

## Sheet2
Priority | Rationale | Planned Start | Status
Primary | Top priority; mission-critical; pre-requisite for other initatives | Year 1 (2020-2021) | Completed
Secondary | Important but not mission-critical; defer for year 1 | Year 2 (2021-2022) | In-progress
Tertiary | Requires other actions first; defer for year 1 | Year 3 (2022-2023) | Pending start
Deferred